## Sheet1
Project | Task | Date | Remarks
BBBY-PMall | Test Execution/Defect Documentation/Defect Retest/Testing | 07/08/2019 | 1. Performed ad-hoc testing on different tickets deployed on Dev environment as part of June Release. 2. Updated testing status report for June release. Please find attached sheet with updated Ticket-Wise Test Summary, Test Case Execution Summary, Test cases and Defects created in June release till date. Also shared detailed status in a separate email. 3. Attended daily status meeting to discuss project updates, tasks , observations and requirements.
BBBY-PMall | Test Execution/Defect Documentation/Defect Retest/Testing | 07/09/2019 | 1. Retested defects assigned to me in PMall admin. Shared detailed status in a separate email, attached here for reference. 2. Created defects #7890 and #7891 based on discussion on yesterday’s observations and assigned them to Sonny. 3. Worked on verification of more pages as per Sonny’s confirmation on scope of ticket #6791 - Mobile round corner block refresh. Will share observations if any once complete. 4. Updated testing status report for June release. Please find attached sheet with updated Ticket-Wise Test Summary, Test Case Execution Summary, Test cases and Defects created in June release till date. Also shared detailed status in a separate email.
BBBY-PMall | Test Execution/Defect Documentation/Defect Retest/Testing | 07/10/2019 | 1. Performed regression test on live environment on both mobile and desktop site. No issues found. Shared status in a separate email. 2. Retested defect #7746 on dev environment which is failing retest. Assigned it back to Sonny for review. Will update the same as per our discussion in today’s stand-up call. 3. Verified 3 new pages as part of #6791 on dev environment. Shared observations with Sonny and you on email. Please review and let me know if defects need to be created against them. 4. Reviewed errors appearing in Bug snag tool. Need to discuss the same to identify the priority and where to raise them. 5. Attended daily status meeting to discuss project updates, tasks , observations and requirements. 6. Will reschedule daily stand-up call to 11:15 AM(Chicago time), yesterday onwards. 7. Updated testing status report for June release. Please find attached sheet with updated Ticket-Wise Test Summary, Test Case Execution Summary, Test cases and Defects created in June release till date. Also shared detailed status in a separate email.
BBBY-PMall | Test Execution/Defect Documentation/Defect Retest/Testing | 07/11/2019 | 1. Retested defect #7746 again on dev environment which is failing retest on dev as well for issue 2. Assigned it to you for review. Please review and suggest. 2. Created defects #7900, #7901, #7902 in PMall admin as per Sonny’s response on yesterday’s observations. 3. Retested defects #7815 and #7817. Please respond on query shared regarding defect #7817. 4. Verified “Re-order This Item” functionality from Order Details page on mobile site as part of #6791. Shared observations with Sonny for review. 5. Attended daily status meeting to discuss project updates, tasks , observations and requirements. 6. Updated testing status report for June release. Please find attached sheet with updated Ticket-Wise Test Summary, Test Case Execution Summary, Test cases and Defects created in June release till date. Also shared detailed status in a separate email.
BBBY-PMall | Test Execution/Defect Documentation/Defect Retest/Testing | 07/12/2019 | 1. Created defect #7907 for the production issue(Access Denied on CreateProfile.aspx page). Tried to reproduce the issue in different ways, but not able to reproduce it here. Please refer the mail sent for details. 2. Created defect #7908 as per yesterday’s observations shared with Sonny and assigned it to him in PMall admin. 3. Worked on creation of Life Cycle for a Project/Feature/Defect in PMall admin. Shared the initial draft in separate email. Please review and suggest. 4. Tried to reproduce the other production issue reported yesterday for iPad, but not able to reproduce that too. Please refer the email shared for more details. Also, attached the same here for reference. 5. Attended daily status meeting to discuss project updates, tasks , observations and requirements. 6. Updated testing status report for June release. Please find attached sheet with updated Ticket-Wise Test Summary, Test Case Execution Summary, Test cases and Defects created in June release till date.